Healthcare Appointment & Follow-up Manager

Complete Project Build Plan — Chunked Task Breakdown

Prepared by: Artemis

Version 1.0

August 2026

# 1. How to Use This Plan

This replaces the seven broad phases in the SDP with 22 small, doable chunks that span the full stack — database, backend API, background workers, and all three frontend portals together. Each chunk ends in something you can actually demo, not just code that compiles. Chunks are numbered in build order: later chunks depend on earlier ones, but chunks within the same stage (marked by the shaded headers below) can be reordered against each other if one is blocked.

- S = a focused 1–2 hour session

- M = half a day

- L = a full day — usually because it involves concurrency, an external API, or both

Frontend UI for a feature is bundled into the same chunk as its backend, not built separately — wiring a screen to mock data and then rewiring it to a real endpoint later is wasted work. The one exception is Chunk 4, the shared design system, which every screen after it depends on.

## Stage A — Foundations

| Chunk 1 | Repo Scaffold & Environment | DevOps | S |
| --- | --- | --- | --- |

Includes:

- Monorepo or two-package structure: api (Flask) + worker entry point (Celery) sharing the same codebase, web (Next.js)

- .env.example covering DB, Redis, Claude API key, SendGrid key, Google OAuth client

- Base deploy pipeline stood up early: Vercel (web) + Render/Railway (api + worker) + managed Postgres + managed Redis, even before there's anything real to deploy

Depends on:  Nothing

Done when:  An empty “Hello API” and an empty Next.js page are both live on public URLs — deployment risk is retired on day one, not day fourteen

| Chunk 2 | Database Schema & Migrations | Backend | S |
| --- | --- | --- | --- |

Includes:

- All tables from §4 of the Design Document: user, patient_profile, doctor_profile, doctor_leave, appointment, symptom_summary, visit_note, prescription_item, medication_reminder, notification, calendar_event

- The partial unique index on (doctor_id, appt_date, slot_start) and the other three indexes from §4.1

Depends on:  Chunk 1

Done when:  Migrations run clean on a fresh database; the partial unique index exists and is confirmed with a manual duplicate-insert test in psql

| Chunk 3 | Auth Module — API + Screens | Full-stack | M |
| --- | --- | --- | --- |

Includes:

- Register/login endpoints, JWT + refresh token issuance, bcrypt hashing, role claim

- Role middleware enforced on every route from here on, not bolted on later

- Login and register screens, role-aware redirect after login

Depends on:  Chunk 1, 2

Done when:  You can register as a patient, log in, and get redirected to a role-appropriate empty home screen; a patient token is rejected by a doctor-only route

| Chunk 4 | Design Tokens & Shared Component Library | Frontend | M |
| --- | --- | --- | --- |

Includes:

- Color, type, and spacing tokens from §2 of the Frontend Design Document, wired as CSS variables / Tailwind theme

- Base components: Button, Input, TextArea, Card, Table, Badge (urgency + status), Toast

- The vitals-line SVG divider component; app shell/nav per portal

Depends on:  Chunk 1

Done when:  A static style-guide page renders every component in every state with no real data behind it

## Stage B — Doctor & Admin Core

| Chunk 5 | Doctor & Admin Profile Management | Full-stack | M |
| --- | --- | --- | --- |

Includes:

- Admin CRUD API for doctor profiles: specialisation, working hours, slot duration

- Admin doctors table + create/edit form UI

Depends on:  Chunk 3, 4

Done when:  An admin can create a doctor profile through the UI and see it appear in the table — no leave logic yet

| Chunk 6 | Doctor Leave Marking (basic) | Full-stack | S |
| --- | --- | --- | --- |

Includes:

- POST /doctors/{id}/leave without conflict handling yet — just the insert

- Doctor/Admin schedule UI: working hours editor + mark-leave control

Depends on:  Chunk 5

Done when:  A leave date can be marked and shows up on the doctor's schedule; conflict handling is deliberately deferred to Chunk 11

## Stage C — Booking Engine (the correctness-critical core)

| Chunk 7 | Availability Search | Full-stack | M |
| --- | --- | --- | --- |

Includes:

- GET /doctors?specialisation= and GET /doctors/{id}/availability?date= (working hours − leave − bookings)

- Patient search screen + doctor profile screen with a calendar of available dates

Depends on:  Chunk 5

Done when:  A patient can filter by specialisation and land on a doctor profile showing real computed availability, not mock data

| Chunk 8 | Slot Hold Mechanism | Full-stack | L |
| --- | --- | --- | --- |

Includes:

- POST /appointments/hold: Redis NX lock (§7 of the Design Document) + appointment row with status='held'

- Background sweeper (every 30s) expiring stale holds

- Patient slot-picker UI: slot grid, live countdown (mm:ss, depleting bar, coral under 60s), symptom form

Depends on:  Chunk 7

Done when:  Selecting a slot starts a real countdown backed by the actual Redis TTL; letting it expire releases the slot, visible on a second browser/session picking it up

| Chunk 9 | Booking Confirm & Double-Booking Guarantee | Backend | M |
| --- | --- | --- | --- |

Includes:

- POST /appointments/{id}/confirm inside the partial-unique-index guard (§6)

- 409 Conflict handling surfaced as a clear message in the Patient UI, not a raw error

Depends on:  Chunk 8

Done when:  A concurrency test — firing simultaneous confirm requests for the same slot — shows exactly one succeeds and the rest get a friendly “slot no longer available” message

| Chunk 10 | Cancel & Reschedule | Full-stack | S |
| --- | --- | --- | --- |

Includes:

- DELETE /appointments/{id} for patient and doctor

- Appointment detail screen: status, reschedule/cancel actions

Depends on:  Chunk 9

Done when:  A patient can cancel a confirmed appointment and it disappears from the doctor's queue

| Chunk 11 | Doctor Leave Conflict Handling | Full-stack | M |
| --- | --- | --- | --- |

Includes:

- The FOR UPDATE transaction from §8: lock confirmed appointments on the leave date, insert leave, cascade-cancel affected rows

- Admin leave-marking UI: the conflict warning shown in §4.3 of the Frontend Design Document when confirmed appointments exist on the chosen date

Depends on:  Chunk 6, 9

Done when:  Marking leave on a date with confirmed bookings shows the warning, requires explicit confirm, and the affected appointments flip to leave_cancelled

## Stage D — AI Summaries

| Chunk 12 | Pre-Visit LLM Summary | Full-stack | L |
| --- | --- | --- | --- |

Includes:

- Celery worker process scaffold, Redis as broker (shared by this and Stage E)

- Symptom submission endpoint → queued job → Claude call with the JSON-constrained prompt from §10.1, llm_status state machine, 3 retries

- Doctor today-queue UI with urgency badges + appointment detail showing the summary front-and-center, raw symptoms collapsed

Depends on:  Chunk 9

Done when:  Submitting symptoms produces a real urgency/chief-complaint/questions summary in the doctor's view within a few seconds; a simulated API failure still leaves the raw symptoms visible with the fallback message from §6

| Chunk 13 | Post-Visit LLM Summary | Full-stack | M |
| --- | --- | --- | --- |

Includes:

- Doctor visit-notes + prescription entry endpoint → queued job → Claude call with the §10.2 prompt

- Patient post-visit summary card + medication schedule display

Depends on:  Chunk 12

Done when:  Submitting visit notes produces a patient-friendly summary the patient can see, with the same graceful-fallback behaviour on a forced failure

## Stage E — Notifications, Calendar, Reminders

| Chunk 14 | Email Notification Pipeline | Backend | L |
| --- | --- | --- | --- |

Includes:

- SendGrid integration: booking confirmation, reminder, cancellation, leave-notice templates

- Retry/backoff (1m, 5m, 30m; permanent-failure after 5 attempts) per §9.1

- Admin notifications table: status per job + manual retry action for permanently-failed jobs

Depends on:  Chunk 9, 11

Done when:  Booking a real appointment sends a real confirmation email to both patient and doctor; killing the SendGrid key doesn't block booking and shows a failed row in the admin table

| Chunk 15 | Google Calendar Integration | Backend | M |
| --- | --- | --- | --- |

Includes:

- OAuth 2.0 connect flow for patient and doctor

- Event create on booking, update on reschedule, delete on cancellation/leave, through the same worker/queue pattern

Depends on:  Chunk 14

Done when:  A confirmed booking creates a real event on both a test patient and doctor Google Calendar; cancelling it removes the event

| Chunk 16 | Medication Reminders | Backend | S |
| --- | --- | --- | --- |

Includes:

- Reminder scheduling from prescription_item.frequency at post-visit-summary time

- Reminder worker + email send through the Chunk 14 pipeline

Depends on:  Chunk 13, 14

Done when:  A test prescription with a short frequency produces a reminder email at the scheduled time without manual triggering

## Stage F — Remaining Screens & Admin Overview

| Chunk 17 | Patient Home & Account | Frontend | S |
| --- | --- | --- | --- |

Includes:

- Home: upcoming appointment summary + “Find a doctor” entry point

- Account: profile fields, notification preferences

Depends on:  Chunk 10, 13

Done when:  Patient portal is now navigable end-to-end from login through a completed appointment

| Chunk 18 | Admin Overview Dashboard | Frontend | S |
| --- | --- | --- | --- |

Includes:

- Booking volume, failed-job count, at-a-glance system health, pulling from the notification and appointment tables

Depends on:  Chunk 14

Done when:  The dashboard reflects real counts from the database, not placeholder numbers

## Stage G — Hardening & Ship

| Chunk 19 | Concurrency & Failure Test Suite | Backend | M |
| --- | --- | --- | --- |

Includes:

- Automated test: N simultaneous hold+confirm on one slot → exactly one succeeds

- Automated test: forced external-call failure → correct backoff timing and fallback UI state

Depends on:  Chunk 9, 12, 14

Done when:  Tests pass consistently across repeated runs, not just once

| Chunk 20 | Accessibility & Responsive Polish | Frontend | M |
| --- | --- | --- | --- |

Includes:

- Keyboard focus rings, AA contrast check on coral/amber text, reduced-motion behaviour

- Patient portal down to mobile width; doctor/admin down to tablet width

Depends on:  All Stage A–F chunks

Done when:  Every screen in all three portals passes the §7 accessibility checklist from the Frontend Design Document

| Chunk 21 | Deployment & Smoke Test | DevOps | S |
| --- | --- | --- | --- |

Includes:

- Final env var pass across Vercel/Render/Railway, production Postgres + Redis, production API keys

- Full manual walk-through on the live URL: register → book → leave conflict → visit notes → email → calendar

Depends on:  Chunk 19

Done when:  The hosted URL supports a complete booking-to-follow-up journey with no local-only dependencies

| Chunk 22 | Documentation | DevOps | M |
| --- | --- | --- | --- |

Includes:

- README: setup guide, .env.example, API docs, DB schema, LLM prompts, Google Calendar setup steps

- System Design write-up finalised (§12 of the Design Document, already ≤800 words)

Depends on:  Chunk 21

Done when:  A fresh clone + README alone is enough for someone else to run the project locally, matching Deliverable 2 of the assignment brief

# 2. Mapping Back to the SDP

For reference against the original 7-phase SDP: Chunks 1–4 ≈ SDP Phase 1; Chunks 5–6 ≈ Phase 2; Chunks 7–11 ≈ Phase 3; Chunks 12–13 ≈ Phase 4; Chunks 14–16 ≈ Phase 5; Chunks 17–20 ≈ Phase 6; Chunks 21–22 ≈ Phase 7. The chunks don't change the plan, they just make each phase small enough to start without deciding how to spend an entire multi-day block at once.