Healthcare Appointment & Follow-up Manager

Software Development Plan (SDP)

Prepared by: Artemis

Version 1.0

August 2026

# 1. Purpose

This plan lays out how the Healthcare Appointment & Follow-up Manager will be built, tested, and delivered: development approach, phased timeline, resourcing, risks, testing strategy, and a checklist mapping directly to the assignment's deliverables and evaluation criteria. It complements the System Design Document, which covers the technical ‘how’; this covers the ‘in what order, by when, and what could go wrong.’

# 2. Development Approach

Solo developer, single deployable codebase (modular monolith + one worker process), built iteratively module-by-module rather than big-bang. Each phase below ends in a runnable, demoable state — not just merged code — so the project is never more than a few days from a working checkpoint. Git is used with feature branches per module and small, frequent commits.

- Methodology: lightweight iterative/incremental, not formal Scrum — appropriate for a one-person team.

- Definition of ‘done’ per phase: feature works end-to-end through the UI, has at least a smoke test, and is committed with a clear message.

- Environment parity: same .env-driven config locally and in hosted deployment from Phase 1 onward, to avoid late ‘works on my machine’ surprises.

# 3. Phased Timeline

Seven phases. Durations assume part-time work alongside placement season — adjust to your actual calendar; the ordering and dependencies matter more than the exact day counts.

| Phase | Scope | Exit criteria |
| --- | --- | --- |
| 1. Foundations (Days 1–2) | Repo scaffold, Postgres schema + migrations, JWT auth (register/login), role middleware, base deploy pipeline (Vercel + Render) | Can register/login as patient/doctor/admin; empty app is live on a public URL |
| 2. Doctor & Admin core (Days 3–4) | Admin CRUD for doctor profiles (specialisation, working hours, slot duration); doctor leave marking (no conflict logic yet) | Admin can create a doctor; doctor can log in and see their profile |
| 3. Booking engine (Days 5–7) | Availability computation, Redis slot-hold, partial unique index, hold→confirm flow, cancellation, leave-conflict transaction (§6–§8 of the design doc) | Two simultaneous booking attempts for the same slot: exactly one succeeds; marking leave on a booked date cancels + flags affected appointments |
| 4. LLM integration (Days 8–9) | Symptom form → pre-visit summary job; visit-notes form → post-visit summary job; JSON-constrained prompts, llm_status state machine, retry logic, raw-text fallback UI | Doctor sees urgency + chief complaint + questions before a visit; patient sees a friendly summary after; simulated LLM failure still leaves both records usable |
| 5. Notifications & Calendar (Days 10–12) | Celery queue + worker process (Redis broker); SendGrid emails (confirmation/reminder/cancellation/leave notice); Google Calendar OAuth + event create/update/delete; medication reminder scheduling from prescription frequency | Booking triggers an email and a calendar event on both real accounts; killing the email/calendar API key doesn't break booking |
| 6. Hardening & testing (Days 13–14) | Concurrency test for double-booking, retry/backoff test with simulated failures, role-auth edge cases, input validation pass, error-shape consistency | All core flows pass manual QA across all three portals; automated tests for the booking race condition pass consistently |
| 7. Docs & deployment (Day 15) | README (setup, .env.example, API docs, DB schema, LLM prompts, Google Calendar setup), final hosted deploy, System Design write-up finalised | A fresh clone + README alone is enough for someone else to run the project locally |

# 4. Resource Plan

## 4.1 Team

Single developer (Artemis) acting as full-stack engineer, DB designer, and QA. No dedicated reviewer — mitigated by writing smoke tests per phase and doing a self-review pass before each phase is marked done.

## 4.2 Tooling

- Frontend: React / Next.js, deployed on Vercel

- Backend + worker: Python (Flask) + Celery, deployed on Render/Railway

- Data: managed PostgreSQL (Neon/Supabase/Render) + managed Redis

- External APIs: Claude API (LLM), SendGrid (email), Google Calendar API (OAuth 2.0)

- Source control: Git/GitHub, feature branches per module

# 5. Risk Management

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Concurrency bug lets two patients book the same slot | Medium | High — core requirement fails | Partial unique index as the authoritative guard (not just the Redis lock); dedicated concurrency test in Phase 6 |
| Google Calendar OAuth setup eats more time than budgeted | High | Medium — delays Phase 5 | Do a throwaway OAuth spike in Phase 1 to de-risk consent-screen/redirect-URI setup before it's on the critical path |
| LLM API rate limits or malformed JSON responses during demo | Medium | Medium — could look like a broken feature live | response_format constrained to JSON, retries with backoff, and a visible raw-notes fallback so a failure never reads as a blank screen |
| Free-tier hosting sleeps the worker process | Medium | Medium — reminders/retries silently stop | Confirm the chosen host's always-on behavior in Phase 1; add a lightweight health-check ping if needed |
| Time crunch from overlapping placement interviews | High | Medium — schedule slips | Phases are ordered so that stopping after any phase still leaves a demoable app; Phase 3 (booking correctness) is prioritised over polish |
| Scope creep (e.g. SMS reminders, multi-language UI) | Medium | Low–Medium | Everything beyond the brief goes on a written ‘nice to have’ list, not into the Phase 1–7 plan |

# 6. Testing Strategy

## 6.1 Automated

- Unit tests for slot-availability computation (working hours − leave − existing bookings).

- Concurrency/integration test: fire N simultaneous hold+confirm requests at the same slot, assert exactly one commits and the rest get 409.

- Worker retry test: force an external call to fail N times, assert backoff timing and the permanent-failure threshold (5 attempts).

- LLM fallback test: force a malformed/failed LLM response, assert llm_status='failed' and the raw text remains visible.

## 6.2 Manual QA

- Full booking journey per portal: register → search → hold → symptom form → confirm → email + calendar check.

- Leave-conflict journey: admin marks leave on a date with a confirmed booking → patient receives a cancellation notice → calendar event removed.

- Auth/role boundary checks: a patient JWT cannot hit doctor/admin-only routes, and vice versa.

- Cross-browser/basic responsive pass on all three portals before the final hosted deploy.

# 7. Deliverables Checklist

Mapped directly to the assignment brief so nothing is missed at submission time.

| Deliverable | Status target by Phase 7 |
| --- | --- |
| Zip file with complete source code | Repo exported, .env and node_modules excluded |
| README: setup guide, .env.example, API docs, DB schema, LLM prompts, Google Calendar setup steps | Written and verified against a clean clone |
| Hosted application URL | Live on Vercel + Render/Railway, smoke-tested post-deploy |
| System design write-up (≤800 words): double-booking, leave conflicts, slot hold, notification failure handling | Finalised — see System Design Document §12 |

# 8. Evaluation-Focus Self-Check

Before submission, walk back through the brief's own evaluation focus areas and confirm each is demonstrably true, not just implemented:

- Problem-solving on slot conflicts, leave management, notification reliability — covered by §6–§9 of the design doc and the Phase 6 tests.

- LLM prompt quality and failure handling — covered by §9.2 and §10.

- Database schema design — covered by §4; check FKs and the partial unique index actually exist in the deployed DB, not just in the migration file.

- API design and code structure — module boundaries from §2.1 should be visible in the folder structure, not just on paper.

- Email and Google Calendar integration — test against real inboxes/calendars, not just logs, right before submission.

- Documentation — have someone else (or a fresh clone) follow the README with zero prior context.